WEEK 4 TASK

Monitoring, Reporting,
and Process Improvement

Customer Churn Prediction Using Python and Machine Learning

Prepared By: Amrutha T
Role: Data Science Project Coordinator
Task Period: 8–14 September 2026
Overall Project Horizon: 5 Weeks

| Item | Project detail |
| --- | --- |
| Project objective | Analyze historical customer data and develop a classification model to identify customers likely to discontinue a service. |
| Dataset | IBM Telco Customer Churn sample dataset |
| Dataset size | 7,043 customer records and 21 fields |
| Target | Churn |
| Core tools | Python, Pandas, NumPy, Matplotlib, Seaborn, Scikit-learn, Jupyter/Google Colab, Git/GitHub |
| Week 4 focus | Monitor progress, data quality, model validation, quality gates, risks, reporting and improvement actions. |

Evidence-first principle: planned values are not reported as executed results. Actual model metrics must come from the executed notebook.

# 1. Executive Summary

This Week 4 report converts the Customer Churn Prediction project into a measurable monitoring and reporting system. The plan responds directly to the weaknesses identified in Weeks 1–3: insufficient concrete numbers, limited worked examples, less explicit timeline detail, insufficiently detailed risk management, and lack of specific testing and quality-gate evidence.

Week 1 established the business problem, scope, stakeholders and project lifecycle. Week 2 established the IBM Telco Customer Churn dataset, measurable data-quality controls and preprocessing rules. Week 3 established the model-development workflow, 80/20 stratified split with random_state=42, comparison of at least two classification models, required validation metrics, code review, testing, version control and quality gates. Week 4 therefore focuses on monitoring whether these commitments are being met and whether the project is ready to move toward final evaluation.

## Feedback-to-improvement response

| Earlier feedback | Week 4 response |
| --- | --- |
| Week 1: lacked specific data, worked examples and detailed timeline. | Concrete KPI definitions, formulas, thresholds, worked Python examples and dated Week 4 + five-week schedule. |
| Week 2: needed concrete examples and detailed risk management; transformations needed executed evidence. | Evidence register, risk matrix with triggers/actions/owners, and explicit separation of executed evidence from planned examples. |
| Week 3: lacked actual execution outputs/numbers; testing and quality gates needed more detail. | Actual model values are left for executed notebook output; testing matrix, quality gates, acceptance criteria and corrective-action protocol are detailed. |

# 2. Week 4 Requirement-to-Evidence Map

| Task requirement | Where addressed | Evidence / output |
| --- | --- | --- |
| Outline KPIs | Section 3 | KPI table with formula, target, frequency, owner and status. |
| Python tools for tracking metrics | Section 5 | Libraries, purposes and worked metric-calculation examples. |
| Reporting mechanism | Section 7 | Daily/weekly/monthly reporting schedule and stakeholders. |
| Evaluate performance and initiate corrections | Section 8 | Deviation thresholds, severity, root-cause analysis and corrective actions. |
| Flowcharts / dashboards | Sections 6 and 10 | Dashboard wireframe and monitoring flowchart. |
| Process improvement / strategy adjustment | Section 9 | Evidence-based proposal and approval process. |

# 3. KPI Framework

KPIs are divided into schedule, data quality, model performance, software/reproducibility, risk and reporting categories. Targets are project-control thresholds rather than claimed achieved results.

| Category | KPI | Calculation / evidence | Target | Frequency | Owner |
| --- | --- | --- | --- | --- | --- |
| Schedule | Milestone completion | Completed milestones / planned milestones ×100 | ≥95% | Weekly | Coordinator |
| Schedule | On-time task rate | On-time tasks / due tasks ×100 | ≥90% | Weekly | Coordinator |
| Data | Dataset row count | Count of records in approved dataset | 7,043 baseline | Each run | Data Analyst |
| Data | Field count | Number of columns in approved schema | 21 baseline | Each run | Data Analyst |
| Data | Completeness | Non-null required values / required values ×100 | ≥98% | Weekly | Data Analyst |
| Data | Duplicate rate | Duplicate rows / total rows ×100 | ≤1% | Weekly | Data Analyst |
| Data | Validation error rate | Invalid rows / total rows ×100 | ≤2% | Weekly | Data Analyst |
| Model | Accuracy | Correct predictions / all predictions | Actual output required | Weekly | Data Scientist |
| Model | Precision | TP / (TP+FP) | Actual output required | Weekly | Data Scientist |
| Model | Recall | TP / (TP+FN) | Actual output required | Weekly | Data Scientist |
| Model | F1-score | 2 × Precision × Recall / (Precision+Recall) | Actual output required | Weekly | Data Scientist |
| Model | ROC-AUC | Area under ROC curve using prediction scores | Actual output required | Weekly | Data Scientist |
| Model | Confusion matrix | TN, FP, FN, TP counts | Required evidence | Weekly | Data Scientist |
| Model quality | Train-validation gap | Training score minus validation score | Investigate material gap | Weekly | Data Scientist |
| Reproducibility | Rerun consistency | Same data/seed/environment produces consistent output | PASS | Weekly | ML Engineer |
| Testing | Critical test pass rate | Passed critical tests / total critical tests ×100 | 100% | Weekly | ML Engineer |
| Risk | Open high/critical risks | Count of unresolved high/critical risks | 0 preferred | Weekly | Coordinator |
| Actions | Overdue corrective actions | Count of actions past due date | 0 preferred | Weekly | Coordinator |

# 4. Concrete KPI Scorecard and Worked Interpretation

The following scorecard demonstrates exactly how the monitoring report should look. Values that can be established from the project documentation are labelled as baseline/target; model-performance values are deliberately marked 'PENDING EXECUTION' because Week 3 requires actual notebook output before any metric is claimed.

| KPI | Baseline / Example | Target | Status rule | Current reporting status |
| --- | --- | --- | --- | --- |
| Dataset records | 7,043 | 7,043 approved baseline | PASS if expected dataset version is loaded | Baseline confirmed from project documentation |
| Dataset fields | 21 | 21 | PASS if schema matches | Baseline confirmed from project documentation |
| Completeness | Example: 98.7% | ≥98% | Green ≥98%; Amber 95–97.9%; Red <95% | Illustrative example only; replace with executed Week 4 output |
| Duplicate rate | Example: 0.6% | ≤1% | Green ≤1%; Red >1% | Illustrative example only; replace with executed output |
| Accuracy | PENDING EXECUTION | Project-approved target | Compare actual result with target | Not claimed until executed |
| Precision | PENDING EXECUTION | Project-approved target | Compare actual result with target | Not claimed until executed |
| Recall | PENDING EXECUTION | Project-approved target | Compare actual result with target | Not claimed until executed |
| F1-score | PENDING EXECUTION | Project-approved target | Compare actual result with target | Not claimed until executed |
| ROC-AUC | PENDING EXECUTION | Project-approved target | Compare actual result with target | Not claimed until executed |
| Critical tests | PENDING EXECUTION | 100% pass | Any critical failure blocks acceptance | Not claimed until executed |

Interpretation example: if an executed completeness check returns 98.7%, the KPI is above the 98% threshold and is Green. If a future executed F1-score is below the approved target, the report should show Red/Amber status, document the gap, identify the root cause, assign a corrective action and re-measure after the change. The example numbers above are not presented as actual execution results.

# 5. Python-Based Monitoring and Reporting

Python is used to turn raw outputs and validation results into repeatable monitoring evidence. The monitoring notebook should be rerunnable and should save its tables/plots so that each weekly report can be traced to a specific dataset version, code version and execution date.

| Tool | Specific Week 4 use |
| --- | --- |
| Pandas | Read KPI/result files, calculate rates, compare current values with targets, create report tables. |
| NumPy | Numerical calculations and array operations. |
| Scikit-learn | Accuracy, precision, recall, F1, ROC-AUC and confusion matrix. |
| Matplotlib | KPI trend plots and model-comparison charts. |
| Seaborn | Confusion-matrix heatmap and distribution/quality plots. |
| Jupyter / Google Colab | Reproducible execution record with visible outputs. |
| Git/GitHub | Version-control monitoring code, notebook and report evidence. |
| Python logging | Record run date, warnings, failures and corrective-action references. |

## 5.1 Worked Python example — model KPI calculation

from sklearn.metrics import (
    accuracy_score, precision_score, recall_score,
    f1_score, roc_auc_score, confusion_matrix
)

accuracy = accuracy_score(y_test, y_pred)
precision = precision_score(y_test, y_pred, zero_division=0)
recall = recall_score(y_test, y_pred, zero_division=0)
f1 = f1_score(y_test, y_pred, zero_division=0)
roc_auc = roc_auc_score(y_test, y_prob)
cm = confusion_matrix(y_test, y_pred)

print("Accuracy:", round(accuracy, 4))
print("Precision:", round(precision, 4))
print("Recall:", round(recall, 4))
print("F1-score:", round(f1, 4))
print("ROC-AUC:", round(roc_auc, 4))
print("Confusion matrix:\n", cm)

## 5.2 Worked Python example — automated KPI status

def status(value, target, direction="ge"):
    if direction == "ge":
        return "GREEN" if value >= target else "RED"
    return "GREEN" if value <= target else "RED"

completeness = df["required_field"].notna().mean() * 100
duplicate_rate = df.duplicated().mean() * 100

print("Completeness:", round(completeness, 2), "%",
      status(completeness, 98, "ge"))
print("Duplicate rate:", round(duplicate_rate, 2), "%",
      status(duplicate_rate, 1, "le"))

These code blocks are worked examples of the monitoring mechanism. They are not evidence that the outputs were executed in this document.

# 6. Testing Strategy and Quality Gates

To address the Week 3 feedback, monitoring includes explicit tests and acceptance gates. A failed critical gate blocks acceptance until the issue is corrected and the test is rerun.

| ID | Test | Acceptance criterion | Result | Owner |
| --- | --- | --- | --- | --- |
| T01 | Schema test | Expected 21 fields present; unexpected fields reviewed | PASS/FAIL | Data Analyst |
| T02 | Row-count test | Approved dataset contains expected 7,043 baseline records, unless a documented version change exists | PASS/FAIL | Data Analyst |
| T03 | Missingness test | Required-field completeness ≥98% | PASS/FAIL | Data Analyst |
| T04 | Duplicate test | Duplicate rate ≤1% | PASS/FAIL | Data Analyst |
| T05 | Target test | Churn labels contain only approved classes and mapping is correct | PASS/FAIL | Data Analyst |
| T06 | Leakage test | customerID excluded; target-derived/test-informed features excluded | PASS/FAIL | Data Scientist |
| T07 | Split test | 80/20 stratified split with random_state=42 is evidenced | PASS/FAIL | Data Scientist |
| T08 | Pipeline test | Learned preprocessing is fitted only on training data | PASS/FAIL | Data Scientist |
| T09 | Metric test | Accuracy, precision, recall, F1, ROC-AUC and confusion matrix produced | PASS/FAIL | Data Scientist |
| T10 | Reproducibility test | Fresh run uses documented environment and fixed seed and gives consistent results | PASS/FAIL | ML Engineer |
| T11 | Code review test | Critical findings resolved before acceptance | PASS/FAIL | Reviewer |
| T12 | Evidence test | Notebook outputs, metric table, model comparison and decision log saved | PASS/FAIL | Coordinator |

## Quality-gate decision rule

PASS: all critical gates pass and no unresolved critical/high issue blocks acceptance.

AMBER: non-critical issue or emerging trend requires a tracked action but does not block progress.

RED: critical gate fails, serious leakage/quality problem exists, or required evidence is missing; stop the affected activity and correct it.

# 7. Dashboard Layout Design

The dashboard is designed as a one-page management view with drill-down evidence available in the monitoring notebook.

| PROJECT HEALTH | DATA QUALITY | MODEL PERFORMANCE | DELIVERY & RISK |
| --- | --- | --- | --- |
| Overall: GREEN/AMBER/RED | Completeness: xx.xx% | Accuracy: xx.xx / pending | Milestones: xx% |
| KPI trend: ↑/→/↓ | Duplicates: xx.xx% | Precision: xx.xx / pending | On-time: xx% |
| Open actions: # | Schema: PASS/FAIL | Recall: xx.xx / pending | High risks: # |
| Last run: date/time | Validation errors: # | F1 / ROC-AUC: pending | Overdue actions: # |

## Dashboard visual requirements

Use KPI cards for current value, target and status.

Use line charts for weekly trends and target thresholds.

Use a confusion-matrix heatmap after actual model execution.

Use a bar chart to compare at least two candidate models using the same validation metrics.

Use an action table for issue severity, owner, deadline and closure evidence.

# 8. Periodic Reporting Mechanism

| Frequency | Activity | Metrics/evidence | Stakeholders | Action |
| --- | --- | --- | --- | --- |
| Daily | Operational check | Data freshness, schema, validation errors, pipeline/test failures | Analyst, Data Scientist, ML Engineer | Immediate escalation for critical failures |
| Tuesday / mid-week | KPI snapshot | Current data/model/test KPIs and emerging trends | Coordinator + technical team | Early correction before weekly review |
| Weekly | Formal Week 4 report | All KPIs, trend charts, quality gates, risks, actions, model comparison | Coordinator, Data Analyst, Data Scientist, Reviewer | Approve corrective actions and priorities |
| 14 Sep | Week 4 gate review | Acceptance checklist, unresolved issues, improvement proposals | Coordinator + Reviewer + Project Lead | Approve Week 5 handoff |
| Final / Week 5 | Final evaluation | Actual validated model metrics, error analysis, recommendations | All key stakeholders | Final acceptance |

## Standard weekly report format

1. Executive summary — overall status and major changes since last report.

2. KPI scorecard — current value, target, variance, trend and status.

3. Data-quality section — row count, field count, completeness, duplicates and validation results.

4. Model section — actual accuracy, precision, recall, F1, ROC-AUC and confusion matrix from executed output.

5. Testing and quality-gate section — pass/fail evidence and unresolved findings.

6. Risk and issue section — new, closed, escalated and overdue risks/actions.

7. Improvement section — proposed changes, expected impact, effort and approval status.

8. Next-period plan — exact tasks, owners and dates.

# 9. Performance Evaluation and Corrective Action Protocol

| Stage | Activity | Required evidence |
| --- | --- | --- |
| 1. Detect | Automated KPI/quality check identifies threshold breach or negative trend. | KPI output / test result |
| 2. Verify | Confirm calculation, source data, code version and execution log. | Validation note |
| 3. Classify | Assign severity based on impact and urgency. | Issue ID + severity |
| 4. Diagnose | Root-cause analysis across data, feature, model, code, schedule or requirement. | RCA note |
| 5. Correct | Assign action, owner and due date. | Action record |
| 6. Re-run | Execute affected Python tests/model evaluation again. | New notebook output |
| 7. Compare | Compare post-correction KPI with baseline and target. | Before/after table |
| 8. Close | Reviewer/Coordinator confirms evidence and updates decision log. | Closure evidence |

## Corrective-action example

Example: If an executed Week 4 data-quality check reports completeness of 96.5% against the 98% threshold, the KPI becomes Amber/Red according to the approved rule. The coordinator first confirms the calculation, then the Data Analyst identifies which fields and records are responsible. If the cause is a new missing-value pattern, the preprocessing/data-acquisition process is corrected. The same quality test is rerun. Closure occurs only when the evidence shows the KPI has returned to the accepted range or an approved exception is documented.

# 10. Detailed Risk Monitoring and Management

| Risk | Trigger | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| Data quality degradation | Missingness >2%, unexpected schema, duplicates >1% | Medium | High | Run validation before every monitoring cycle; investigate source/version change. | Data Analyst |
| Class imbalance | Model appears strong on accuracy but recall/F1 is weak | Medium | High | Use precision/recall/F1/ROC-AUC and confusion matrix; do not select by accuracy alone. | Data Scientist |
| Data leakage | Target-derived/test-informed feature detected | Low | Critical | Feature audit and pipeline controls; remove leakage and rerun affected experiments. | Data Scientist + Reviewer |
| Overfitting | Large train-validation performance gap | Medium | High | Compare training and validation metrics; simplify/tune model; use controlled validation. | Data Scientist |
| Code/test failure | Critical test fails or branch cannot reproduce | Medium | High | Peer review, automated/manual tests, rollback to approved commit. | ML Engineer |
| Reproducibility failure | Fresh run differs unexpectedly or dependencies fail | Medium | High | requirements/environment record, random_state=42, experiment log; freeze and rerun. | ML Engineer |
| Schedule delay | Daily acceptance criterion missed | Medium | Medium | Time-box tasks, track blockers, reprioritize while protecting Week 4/5 milestones. | Coordinator |
| Missing evidence | Required notebook output or decision record absent | Medium | High | Evidence checklist before weekly sign-off; block claim until output is retained. | Coordinator |
| Ethical misuse | Unsupported sensitive inference or inappropriate use proposed | Low | High | Ethics checklist and reviewer approval; block use and escalate. | Coordinator + Reviewer |

# 11. Process Improvement and Strategy Adjustment Proposals

Every material adjustment should be evidence-based. The project should not change the model, preprocessing, KPI target or scope simply because a single result looks unsatisfactory. The team first establishes the problem, identifies the root cause, evaluates alternatives, and then validates the selected change.

Identify the KPI gap or recurring issue.

Quantify its size and project/business impact.

Perform root-cause analysis.

Generate at least one alternative improvement.

Estimate expected benefit, effort, risk and dependencies.

Prioritize using impact-versus-effort.

Obtain approval from the appropriate reviewer/project lead.

Pilot the change where practical and compare against the previous baseline.

Record the result and standardize successful changes.

Continue monitoring to ensure the improvement is sustained.

| Proposal field | What to record |
| --- | --- |
| Problem | KPI gap or recurring issue. |
| Evidence | Actual Python output, chart, test result, log or stakeholder feedback. |
| Root cause | Confirmed cause and supporting analysis. |
| Proposed change | Specific change to data, features, model, code, process or reporting. |
| Expected impact | KPI/business improvement expected. |
| Effort/risk | People, time, technical risk and dependencies. |
| Owner/deadline | Responsible person and completion date. |
| Validation | Metric and acceptance threshold. |
| Decision | Approved, rejected or deferred, with reason. |

# 12. Monitoring → Reporting → Corrective Action Flowchart

START

↓

Collect dataset + notebook outputs + logs

↓

Run Python data-quality / model / test checks

↓

Calculate KPI scorecard

↓

Update dashboard

↓

Compare with target + quality gates

↓

Deviation / failed gate?

↙                         ↘

NO                         YES

↓                           ↓

Continue monitoring      Verify result

↓                           ↓

Weekly report          Classify severity

↓                           ↓

Stakeholder review     Root-cause analysis

↓

Corrective action

↓

Re-run tests

↓

Compare before/after

↓

Improvement verified?

↙             ↘

NO              YES

↓                ↓

Re-diagnose      Close & document

↓

Update process/strategy

↓

REVIEW

# 13. Detailed Week 4 Timeline — 8 to 14 September 2026

| Date | Planned activity | Evidence/output | Owner |
| --- | --- | --- | --- |
| 8 Sep, Tue | Morning: Week 3 handoff review. Afternoon: confirm KPI definitions, targets, evidence checklist and open risks. | Approved KPI register + handoff log | Coordinator / Reviewer |
| 9 Sep, Wed | Run dataset/schema/quality checks; verify approved 7,043-record/21-field baseline or document version change. | Executed quality-check outputs | Data Analyst |
| 10 Sep, Thu | Run model evaluation outputs; calculate accuracy, precision, recall, F1, ROC-AUC and confusion matrix from executed notebook. | Actual metric table + confusion matrix | Data Scientist |
| 11 Sep, Fri | Run testing/reproducibility checks; compare candidate models using identical validation evidence. | Test results + model comparison | Data Scientist / ML Engineer |
| 12 Sep, Sat | Update dashboard; analyze trends, risks, failed gates and overdue actions. | Dashboard + risk/action register | Coordinator |
| 13 Sep, Sun | Develop improvement proposals from evidence; estimate impact, effort and risk. | Improvement proposal table | Coordinator + Team |
| 14 Sep, Mon | Conduct Week 4 review; close/assign actions; approve Week 5 priorities and final-evaluation needs. | Signed-off Week 4 report + Week 5 handoff | Coordinator / Reviewer / Project Lead |

# 14. Explicit Five-Week Project Horizon

| Period | Main activities | Expected evidence |
| --- | --- | --- |
| Week 1 ¦ 18–24 Aug | Business understanding, scope, objectives, stakeholders, risks and milestones. | Planning report |
| Week 2 ¦ 25–31 Aug | Dataset acquisition, profiling, cleaning, preprocessing, quality gates and data handoff. | Data management report |
| Week 3 ¦ 1–7 Sep | Feature pipeline, model training, validation, testing, code review and reproducibility. | Implementation report + executed evidence |
| Week 4 ¦ 8–14 Sep | Monitoring, KPI reporting, model/data quality review, corrective actions and improvement proposals. | Week 4 monitoring/reporting package |
| Week 5 ¦ 15–21 Sep | Final model evaluation, error analysis, recommendations, limitations and final documentation. | Final evaluation report |
| Submission ¦ 22 Sep | Final document and evidence review/submission. | Final submission package |

# 15. Roles and Responsibilities

| Role | Week 4 responsibility |
| --- | --- |
| Project Coordinator | Own KPI definitions, reporting calendar, risk/action log, stakeholder communication and escalation. |
| Data Analyst | Monitor schema, completeness, duplicates, validation errors and data-version consistency. |
| Data Scientist / ML Developer | Generate actual model metrics, confusion matrix, error analysis, model comparison and improvement recommendations. |
| ML Engineer | Maintain reproducibility, testing, versioning, environment and technical monitoring. |
| Reviewer | Review evidence, quality gates, ethics and corrective-action closure. |
| End User / Business Stakeholder | Interpret business implications, confirm requirements and help prioritize improvements. |

# 16. Evidence Package Required for Week 4 Sign-Off

Executed Python monitoring notebook with visible outputs.

Dataset/version reference and 21-field schema check.

Executed data-quality results including completeness and duplicates.

Executed 80/20 stratified split evidence with random_state=42, where applicable.

Actual model validation metrics: accuracy, precision, recall, F1-score and ROC-AUC.

Confusion matrix and model comparison table.

Testing and code-review results.

Reproducibility/environment evidence.

Dashboard/trend charts.

Risk register and corrective-action tracker.

Improvement proposals and approval decisions.

Week 4 decision log and Week 5 handoff.

# 17. Conclusion

This Week 4 plan establishes a measurable control system for the Customer Churn Prediction project. It directly addresses the feedback from Weeks 1–3 by adding concrete KPI definitions and formulas, worked Python examples, explicit testing and quality gates, a detailed risk matrix, a dated Week 4 schedule, a complete five-week horizon, dashboard design, reporting frequencies, corrective-action rules and an evidence-based improvement process.

The report intentionally does not invent model-performance results. The final accuracy, precision, recall, F1-score and ROC-AUC must be copied from the executed Python notebook and linked to the corresponding model/version. This preserves the evidence-first principle already established in Week 3 and prevents unsupported numerical claims.

# 18. Final Submission Checklist

☐ All Week 4 task requirements are addressed.

☐ KPI definitions, formulas, targets, owners and frequencies are included.

☐ Python tools and worked monitoring examples are included.

☐ Dashboard layout and flowchart are included.

☐ Daily/weekly/final reporting mechanism is defined.

☐ Corrective-action protocol and severity rules are included.

☐ Detailed risk-management plan is included.

☐ Testing strategy and quality gates are explicit.

☐ Week 4 daily timeline and complete five-week horizon are included.

☐ Evidence package is defined.

☐ Actual model metrics will be inserted only from executed Python output.

☐ Document reviewed for consistency, formatting and professional presentation.